## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
cZdE4LDclE-bpkGlq0xLuYMAH5ef | Port Research Proj app to Dataiku DSS | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 07/07/2023 | false | false |  |  |  |  | DB Proj;Research Proj;Cloud Proj
mbd7k4Ok60aAz0D46UWDhYMAAFhn | Train junior analysts on QA | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 07/07/2023 | false | false |  |  |  |  | DB Proj
cph6rF5Ot0mqkvMHYg0Iv4MAEAnx | Complete updating internal training tools | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/09/2023 | false | false |  |  |  |  | DB Proj;Research Proj
pQBSBe4sGUm51jel41Zd8YMAGftI | Update FF script | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/09/2023 | false | false |  |  |  |  | Research Proj | Update to make query more efficient utilizing SQL filters before collecting tables.
t3czSIrtyE6rw8rOiu1cxYMADybP | Reach out to client for tools review | Deliverables Execution | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/02/2023 | false | false |  |  |  |  | Cloud Proj | Display side-by-side high-level Tableau dashboard compared to Dataiku DSS Analysis
bDNh3LmSwEGyvAZgEeC8nIMAHOop | Port DB to new data structure | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/19/2023 | false | false |  |  | 0/1 | Re-load the (new) data into the new structure | Cloud Proj
NROWHXHZ5UGWzTEwcfvTb4MACMIp | Create path forward for internal training | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/16/2023 | false | false |  |  |  |  | DB Proj;Research Proj
0dzzgwquwUe9UpoIJIMExIMAH77K | Research for Dataiku DSS demo | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/18/2023 | true | false |  |  | 0/2 | Research Dataiku run tests;Requirements generation | Cloud Proj | weekly due date as the research and testing is on going
xquea1rqaEKloRFH3QKwIYMAGQcu | Cloud Proj Orientation | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/16/2023 | false | false |  |  | 0/3 | Update schema to account for additional table;Develop slide deck;Present to rest of the team | Cloud Proj
yBu9UrMeZUaDNhEtpVyBaIMAEgMU | POC Feedback loop | Deliverables Execution | Not started | Important |  | Lucy Murray | 05/14/2023 |  | 06/30/2023 | false | false |  |  | 0/3 | Retag data;Reach back to request follow-up;Set-up meeting | Research Proj;Prog 2;Prog 3
s5BZZil8qUqjt_VWqWJrGIMACwGB | Produce research proj deliverables | Deliverables Execution | Not started | Important |  | Lucy Murray | 05/14/2023 |  | 06/23/2023 | false | false |  |  | 0/2 | Prog 2 Workbooks;Prog 3 Workbooks | Research Proj;Prog 2;Prog 3
zF2JWL-mOEuxvcEiqNvYL4MAGiRR | QA Prog 2 and Prog 3 data | Deliverables Execution | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/16/2023 | false | false |  |  |  |  | Research Proj;Prog 2;Prog 3
a3JF-XT_1k21Mu83OhLs64MACUCi | Enter Prog 2 and Prog 3 data | Deliverables Execution | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/09/2023 | false | false |  |  |  |  | Research Proj;Prog 2;Prog 3
aJqMJAPRY0iW-rF0LJs8X4MAHf0Q | Preliminary research | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/12/2023 | false | false | 05/14/2023 | Lucy Murray | 3/3 | Confirm data tables;Set-up report;Rip research from resource | Research Proj;Prog 2;Prog 3
bq0wkcZKT0qqZWRSpZaqX4MACM48 | Reach to POCs in re Prog 2 and Prog 3 | Roadblocks/Needs Review | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/16/2023 | false | false |  |  |  |  | Research Proj;Prog 2;Prog 3
tDOz62onXkWIvrrDQuS9aYMADPlv | Research proj Retagging follow-up | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/05/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Update workbook labels;Meet with SME to discuss final factor tagging | Research Proj;Prog 1
UiWJD3XR1kG6FhrsRznCUoMAHZXQ | Add inputs to Quarterly Review Deck | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/05/2023 | false | false | 05/14/2023 | Lucy Murray | 5/5 | Slides 8-9: Colleague 1/Colleague 2;Slides 1-6: Me;Slide 16-19: Me/Colleague 5;Slides 12-15: Colleague 3/Colleague 4;Slide 20: Colleague 6 | DB Proj;Research Proj
eL_KJPKaEEufLY1bnxeyc4MAD_Hn | Evaluate older Git issues | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/31/2023 | false | false |  |  | 0/2 | Meet with colleague to decide if issues should be kept or closed ;Go through projects and comb through old issues | DB Proj;Research Proj
Mv7SFLwYMkCEorCf0t6faIMAEw0e | Review Training modules | BPI | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/12/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | DB Proj;Research Proj | * Make notes of slides that need to be changed or that have confusing information to communicate to senior members of the team later * Save down a new copy of modules that you know need to be updated and create the updates yourself - to be approved by senior members of the team later
5Nufq8kkqk-2paQtSy-9-YMAFYkL | Review SoP doc | BPI | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/12/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Review info;Add examples to Appendix | DB Proj;Research Proj
x0VK5hkhO0aSWjFG4aijHoMAF-30 | Review external training materials that exist | BPI | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/08/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Review materials;Create slide to begin discussion for quaterly review | DB Proj;Research Proj
GSL6E61bP0OAIPT2D89PfYMADQwn | Enter Prog 4 data | Deliverables Execution | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 07/14/2023 | false | false |  |  |  |  | Research Proj;Prog 4
PHj-EKUGFkadQi0-JHJFOoMABlfD | Update Deliverables Scripts | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  | 0/2 | Update styling to ensure that conditional formatting is where it is supposed to be;Validate that potential missing information from DB will not be an issue going forward | Research Proj | Went through the markdown with Andy today (4/10/23) and ran into some issues.
FNoX8aMa9EaOAqSoq_kNKoMAGK9P | S-Curve for Quantities of Interest/Duration | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | Research Proj;Cloud Proj | "How long do definitizations usually take?" Can work to formulate that as a more precise database query.
rBDy97KwCkWhvurr94ZW_IMAB_Xt | Review Prog 1 Program History/Overview Draft and Research | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 04/24/2023 | false | false | 05/14/2023 | Lucy Murray | 3/3 | Review and edit draft;Compile program research into a shared document ;Write a draft of the program overview/history | Research Proj;Prog 1
wNowU9PNskmxTlNPFt29fIMACYrY | Clean KDB by labeling lookup tables correctly | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | DB Proj
EQ63fhRuGEaw4LjEWHMBmoMAAeqr | Fix ETL to handle data update push | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | DB Proj
2qgNBUn0g0CgNpcEM393FoMAEDYk | Import data into Quarto website environment | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 05/09/2023 | false | false | 05/14/2023 | Lucy Murray | 1/1 | Tag-up with team to verify data | Research Proj;Prog 1
9v3mpnTrvUyNLCXcUIYAS4MACDj- | Reach back to POC | Deliverables Execution | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 06/02/2023 | false | false |  |  | 1/2 | Reach out to set up meeting;Finish reading Prog 4 report | Research Proj;Prog 4
s2Ux3rpHQUSNTDXO5a0InoMAHyYy | DB Proj Delivery | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 04/24/2023 | 05/03/2023 | false | false | 05/14/2023 | Lucy Murray | 3/3 | Deliverable 3;Deliverable 1;Deliverable 2 | DB Proj
Ii8jHuJbIUKtk_Gir3jQZYMAFX6g | Enter data priorities | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 |  | 04/21/2023 | false | false | 05/14/2023 | Lucy Murray | 3/3 | Prog 11;Prog 13;Prog 12 | DB Proj
liXb9RlXlk6BWp3ZnKNFLIMAB_Yd | Initial POC/reach out | Roadblocks/Needs Review | Not started | Important |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  | 1/5 | Research POC if possible;Determine POCs;Make initial reach out;Schedule meetings;Create (1) a draft write-up; and (2) read-ahead questions | Research Proj;Prog 4
BtIgFZgJVk-w6alurSGuGIMAFRju | Clean up training materials | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 05/03/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Checklist deck;Training modules | DB Proj;Research Proj
RJr_WO2890GMvbMBB3hijYMAGJki | Review POC brief | BPI | Completed | Important |  | Lucy Murray | 05/14/2023 |  | 03/21/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj | - Review brief - Come prepared with 5-10 key take-aways
i6C0Fk9so0CXOz8fkXVyTYMADnpE | Implement inflation/escalation changes | QoL | Not started | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | DB Proj
oBU533tcGUKu02aB3jW0aoMADf5d | Update Research Proj Documentation | QoL | Not started | Low |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | Research Proj
dvVEJ04h20-h1WNmztyQwoMAH3Zt | Update Miro cartoon | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 03/06/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Dataiku DSS under research proj;Tableau under DB Proj | DB Proj;Research Proj;Cloud Proj
3seG5_GDukOEV1z-F0_sGIMAHfPu | Update and implement file structure | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 03/06/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj
V8mz-u5ASEGc4N3tCug6m4MADv2i | Request research proj review with client | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 04/24/2023 | 05/09/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj;Prog 1
9ft3ogYdjE6CSGL7AryeV4MAFaq3 | Finalize write-ups | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 04/17/2023 | 05/05/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj;Prog 1 | - Plan to finish a week before delivery to provide time for SME feedback
KSBY65b6nUa_cHHMdPofsoMAA0Iz | Meet with next PoC | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 04/14/2023 | 04/21/2023 | false | false | 05/14/2023 | Lucy Murray | 3/3 | Set up meeting;Reach out;Prepare notes for meeting | Research Proj;Prog 1
9JlOA2K5gESWfFSclMw324MAC_R4 | Initial POC/reach out | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 03/06/2023 | 03/13/2023 | false | false | 05/14/2023 | Lucy Murray | 4/4 | Research POC if possible;Determine POCs;Make initial reach out;Schedule meetings | Research Proj;Prog 1
K2-vX9JKvUyHM4EkrSzP1IMAGWgJ | Prog 1 Draft Delivery | Roadblocks/Needs Review | Completed | Important |  | Lucy Murray | 05/14/2023 | 04/24/2023 | 05/12/2023 | false | false | 05/14/2023 | Lucy Murray | 4/4 | Deliverable Item 4;Deliverable Item 3;Deliverable Item 1;Deliverable Item 2 | Research Proj;Prog 1
rnuLJPy6NUGQULlWXyza9YMABRAA | QA for data backfill | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 03/27/2023 | 04/07/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | DB Proj;Research Proj;Prog 1 | - Prog 1 most be complete - Prog 2 is secondary priority afterwards
dJagysOKBkOcGIjXKaw_V4MABFDI | Enter for data backfill | Deliverables Execution | Completed | Important |  | Lucy Murray | 05/14/2023 | 03/01/2023 | 03/31/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | DB Proj;Research Proj;Prog 1 | - Prog 1 must be complete - Prog 2 is secondary priority afterwards
AnVDHnJnaEWbVMgs3PBI2YMAFgC8 | Update DB so empty columns have same type | QoL | Not started | Important |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | DB Proj
88kVWGqprEKLbxJrfeEfgoMAAKFJ | Update metadata for Cloud Proj | Roadblocks/Needs Review | Not started | Important |  | Lucy Murray | 05/14/2023 |  | 06/19/2023 | false | false |  |  |  |  | DB Proj;Cloud Proj
YT_AmGehA0Cpkbx5GAiRcIMAHeNf | Conduct commodity analysis for slide deck | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 02/13/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj
lTKhQl7hlESG-0VCBmEG2YMAEIhf | Feed table into Flatfile | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 02/28/2023 | false | false | 05/14/2023 | Lucy Murray | 1/1 | Choose include_df based on the external data | Research Proj
Lie6xjRMak6-J400U8Ps8IMAGPZF | Update TP research | QoL | Not started | Important |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  | 0/2 | Add dataframes for tables and graphs to print to excel workbook;Plot milestones | Research Proj
btt8HzfY3kmvpwd10bLMY4MAAMfx | Update wb script | BPI | Not started | Medium |  | Lucy Murray | 05/14/2023 |  | 05/26/2023 | false | false |  |  | 0/2 | Finish adding all the necessary graphs;Add in required tables into the Charts tab | Research Proj | Finish adding the rest of the old summary workbook capabilities:
BECEG0DpyEqoCR8nYawgb4MABesr | Clean up deliverables markdown | QoL | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 02/28/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Condense code and source elsewhere (place functions into /Functions folder);Turn creation of summary workbook into functions | Research Proj
TI-dxzfCP0u35WV0MZAy8IMAG5Cd | Update validation checks | QoL | Not started | Low |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  |  |  | DB Proj
h_WFvbEYoE-GJHKBWNk1koMABav7 | Present Research Proj Dataiku DSS Demo | Roadblocks/Needs Review | Not started | Important |  | Lucy Murray | 05/14/2023 | 02/27/2023 | 08/07/2023 | false | false |  |  | 0/3 | Recreated Deliverable 2;Recreated Deliverable 1;RShiny App | Research Proj;Cloud Proj
DuG8qZN1x0yGOzIjaBOuq4MAE3EJ | Automate Flipbook | BPI | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 02/22/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | interactive flipthrough using R;overlay value and quantity | Research Proj
P6Nk7GJ_Yk-vBJ8MHUhw74MABblE | Data backfill priority R script | BPI | Completed | Medium |  | Lucy Murray | 05/14/2023 |  | 02/13/2023 | false | false | 05/14/2023 | Lucy Murray | 2/2 | Reach out to client to confirm weight distribution;Weighted spreadsheet integration | Research Proj
B_zje5cry0WEs4gcMGzsmIMAEifB | Cloud proj Data Requirements | Deliverables Execution | Completed | Medium |  | Lucy Murray | 05/14/2023 |  |  | false | false | 05/14/2023 | Lucy Murray | 0/1 | Requirements what we want to produce at a bronze-silver-gold level data quality | DB Proj;Cloud Proj
5yzlJz1ImEyu7PLT3DtiqoMACUGC | Update entry template | QoL | Not started | Low |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  | 0/1 | Add visual checks | DB Proj
ujf-IJ_Hn0i3nzemFATYbYMAGhru | Cloud tool delivery | Deliverables Execution | Not started | Important |  | Lucy Murray | 05/14/2023 |  | 06/23/2023 | false | false |  |  |  |  | DB Proj;Cloud Proj
-ZpPDVyUm0qLZNuYZjRLF4MAAsVz | Prepare Quarto website environment for deliverables | BPI | Completed | Low |  | Lucy Murray | 05/14/2023 |  | 04/13/2023 | false | false | 05/14/2023 | Lucy Murray |  |  | Research Proj | See full checklist for more detail, but we want (1) text inputs, (2) in-line code inputs to be complete.
XQWzq3OYtEieNgmiVmVPu4MAAYc7 | Automate EDA pulls | QoL | Not started | Low |  | Lucy Murray | 05/14/2023 |  |  | false | false |  |  | 0/4 | add program buckets OR labels to entry tracker;update = TRUE should be involved in this process;draw up EDA visual;write R / PowerAutomate to download multiple cons, place in folders, update Val tracker | DB Proj | script that logs into PIEE->EDA and can grab either a) bulk download b) each individual mod c) conformed contract summary

## Plan name
Plan name | Example Tracker
Plan ID | AtOqUzJ6m0ugbMPeXRQAKYMAE9To
Date of export | 05/14/2023